## Task List
| Project Name | DigiBooks
| Project Manager | Mohit Aswani
| Tech Lead | Palak Goel
| Frontend Developer | Manasvi Agrawal
| UI Desginer | Tiya Bansal
| Tester/ Debugger | Koyna Mittal
| Date | 2021-08-21
WORK BREAKDOWN STRUCTURE - TASKS
Task No. | Task Description | Task Owner | Resources Needed | Task Status | Start Date | Effort (Person hrs) | Complexity Categoy | Actual effort (Person hrs)
1 | Initiation Phase
1.1 | Organizing Group Meet | Mohit Aswani | Google Meet | Complete | 2021-08-21 | 2 |  | 2
1.1.1 | Requirements Discussion | Palak Goel | Google Search, VS Code, Canva | Complete | 2021-08-21 | 1 |  | 1
1.1.3 | Constraints Discussion | Manasvi + Tiya | NA | Complete | 2021-08-21 | 1 |  | 1
2 | Planning Phase (Structure making)
2.1 | Login | Mohit Aswani | Research, Learn from ref. | Assigned
2.1.1 | Welcome Page |  |  |  | 2021-08-23 | 2 | Simple | 2
2.1.2 | Sign Up/ Sign In |  |  |  | 2021-08-24 | 4 | Medium | 2
2.1.3 | Password Re- Set |  |  |  | 2021-08-25 | 4 | Medium | 2
2.2 | Home | Palak Goel | Code Editor, Desgin Softwares | Assigned
2.2.1 | Search |  |  |  | 2021-08-23 | 2 | Simple | 1
2.2.2 | User Profile |  |  |  | 2021-08-24 | 4 | Medium | 3
2.2.3 | Categories |  |  |  | 2021-08-25 | 6 | Complex | 5
2.2.4 | Free Flow Search (Filters) |  |  |  | 2021-08-27 | 4 | Medium | 3
2.2.5 | Settings + Sign Out |  |  |  | 2021-08-28 | 4 | Medium | 2
2.3 | Payment/ Billing | Tiya Bansal | Transaction Knowledge | Assigned
2.3.1 | Debit Card/ Other Payment Modes |  |  |  | 2021-08-25 | 5 | Complex | 3
2.3.2 | Cash on Delivery |  |  |  | 2021-08-27 | 1 | Simple | 1
3 | Execution Phase (Structure Building)
3.1 | App Building | Palak Goel
3.1.1 | Login page | Tiya Bansal | Code Editor, Desgin Softwares | In Progress | 2021-08-23 | 10 | Simple | 6
3.1.2 | Home page | Mansavi | Code Editor, Desgin Softwares | In Progress | 2021-08-23 | 20 | Complex | 14
3.1.3 | Payment/ Billing page | Koyna Mittal | Code Editor, Desgin Softwares | In Progress | 2021-08-25 | 6 | Medium | 4
4 | Control Phase
4.1 | Testing
4.1.1 | Debugging | Koyna Mittal | VS Code, Online Debugger | Assigned | 2021-08-28 | 6 | Medium | 4
4.1.2 | Verification | Mohit Aswani | Constraints should meet | Assigned | 2021-08-29 | 1 | Simple | 1
4.1.3 | Backup Plans | Palak Goel | Re-execution of backup plans | Assigned | 2021-08-29 | 6 | Complex | No need of backup
5 | Close Phase
5.1 | Project Documentation | Mohit Aswani | Canva, PPT | Assigned | 2021-08-29 | 4 | Medium | 5
5.2 | End of Project | Palak Goel | Ending the Project | Assigned | 2021-08-30 | 1 | Medium | 1
5.3 | Submission of Project | Mohit Aswani | Via Mail or Google Drive | Assigned | 2021-08-31 | Less than 1 | Simple | Less than 1